## Project Planner
Project Planner for Prototyping and Systems Engineering (Group B Team 4)
Select a period to highlight at right. A legend describing the charting follows. | [6 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY |  |  | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
| Lead by | Contributors / Supporters | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Coordination, Planning and brainstorming | Daniel C.Chimezie | Betrand Mungu Cho / Riwaj Ghimire | 1 | 5 | 1 | 3 | 100%
Design Model Conceptualization | Daniel C.Chimezie | Betrand Mungu Cho / Riwaj Ghimire | 2 | 3 | 2 | 2 | 100%
Model Design | Betrand Mungu Cho | Daniel C. Chimezie / Riwaj Ghimire | 3 | 6 | 3 | 6 | 100%
Task 1 -GitHub Setup | Daniel C.Chimezie | Betrand Mungu Cho / Riwaj Ghimire | 4 | 1 | 4 | 1 | 100%
Task 1 - Requirements / Diagrams | Riwaj Ghimire | Daniel C. Chimezie / Betrand Mungu Cho | 5 | 2 | 5 | 2 | 100%
Task 2 - Design Model / Simulation | Daniel C.Chimezie | Betrand Mungu Cho / Riwaj Ghimire | 6 | 9 | 6 | 7 | 85%
Task 3 - Coding | Betrand Mungu Cho | Daniel C. Chimezie / Riwaj Ghimire | 7 | 3 | 7 | 6 | 10%
Task 4 - Code Quality Assurance | Daniel C.Chimezie | Betrand Mungu Cho / Riwaj Ghimire | 5 | 4 | 5 | 3 | 10%
Task 5 - Assembly review | Riwaj Ghimire | Daniel C. Chimezie / Betrand Mungu Cho | 5 | 2 | 5 | 5 | 10%
Task 6 - Testing | Daniel C.Chimezie | Betrand Mungu Cho / Riwaj Ghimire | 5 | 2 | 5 | 6 | 10%
Activity 10 |  |  | 6 | 5 | 6 | 7 | 100%
Activity 11 |  |  | 6 | 1 | 5 | 8 | 60%
Activity 12 |  |  | 9 | 3 | 9 | 3 | 0%
Activity 13 |  |  | 9 | 6 | 9 | 7 | 50%
Activity 14 |  |  | 9 | 3 | 9 | 1 | 0%
Activity 15 |  |  | 9 | 4 | 8 | 5 | 1%
Activity 16 |  |  | 10 | 5 | 10 | 3 | 80%
Activity 17 |  |  | 11 | 2 | 11 | 5 | 0%
Activity 18 |  |  | 12 | 6 | 12 | 7 | 0%
Activity 19 |  |  | 12 | 1 | 12 | 5 | 0%
Activity 20 |  |  | 14 | 5 | 14 | 6 | 0%
Activity 21 |  |  | 14 | 8 | 14 | 2 | 44%
Activity 22 |  |  | 14 | 7 | 14 | 3 | 0%
Activity 23 |  |  | 15 | 4 | 15 | 8 | 12%
Activity 24 |  |  | 15 | 5 | 15 | 3 | 5%
Activity 25 |  |  | 15 | 8 | 15 | 5 | 0%
Activity 26 |  |  | 16 | 28 | 16 | 30 | 50%